## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [7 empty] | Total | Critical | High | Moderate | Low | Negligible
| Project title: | Client-Server Based UTM Onboarding System |  | Project Id: | Intern ID: IP-6744 | Project Manager: | Harshada Topale
| DOCUMENT VERSION: |  |  | Last Updated date: |  | Project Team Lead: | ABC
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Email may not be delivered due to SMTP authentication failure | High | Use app-specific password |  | High |  |  | Risk
2 | Risk | Server may not receive client data due to network | Medium | exception handling |  | Moderate |  |  | Assumption
3 | Assumption | java may not installed on device | Medium | Confirm Java is installed |  | Moderate |  |  | Issue
4 | Assumption | wrong input by user | Low | input validation |  | Low |  |  | Dependency
5 | Issue | UTM link contains spaces instead of being URL | Medium | Replaced spaces with underscores using replaceAll(" ", "_") |  | Moderate
6 | Dependency | Availability of JavaMail API | High | Ensure libraries are added |  | High |  |  | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24